## Sheet1
| Start Date | End | Duration = In Days | Task Detail
Project Duration | 2021-01-22 | 2021-04-26 | 94 | PC Solutions Project Started
Project Contract | 2021-01-23 | 2021-01-29 | 6 | Contract done between PC Solutions and Solution Tech Consultants.
Project Scope | 2021-02-01 | 2021-02-12 | 11 | Scope of Project by Solution Tech Consutants for PC Solutions
Feasibility Study | 2021-02-13 | 2021-02-19 | 6 | Study of Feasibility of Project by Solution Tech Consultants for PC Solutions
Security Plan | 2021-02-19 | 2021-03-05 | 14 | Security Plan by Solution Tech Consultants for PC Solutions
Timeline and Schedule | 2021-03-06 | 2021-03-12 | 6 | Timeline and Schedule by Solution Tech Consutants
Database Design | 2021-03-13 | 2021-03-19 | 6 | Database Design by Solution Tech for PC Solutions
User Interface Design | 2021-03-20 | 2021-03-26 | 6 | User Interface Design for PC Solutions.
Data Backup | 2021-03-26 | 2021-03-26 | 1 | Backup of Work done up to now by Solution Tech Consultants for PC Solutions
Software Selection | 2021-03-27 | 2021-04-02 | 6 | Software selected by Solution Tech for PC Solutions
Platform Testing | 2021-04-04 | 2021-04-04 | 1 | Platform Testing at PC Solutions Location
Recommendations | 2021-04-03 | 2021-04-09 | 6 | Final Recommendations by Solution Tech given to PC Solutions
Implementation Plans | 2021-04-03 | 2021-04-09 | 6 | Final Implementation Plans by Solution Tech given to PC Solutions
Training | 2021-03-30 | 2021-04-09 | 10 | Training provided by Solution Tech Consultants for PC Solutions Employees
Implementation | 2021-04-13 | 2021-04-26 | 13 | Day Project Implemented by Solution Tech Consultants and goes live.